## Project Plan and Gantt
Team Members | Amit Walia, Jasmeet Singh, Jashandeep Singh
Project Name | Private/Public Cloud
Project Manager | All
Project Deliverable | Cloud Services
Start Date | 2020-09-29
End Date | 2020-12-04
Overall Progress | 4%
Tasks | Responsible | Start | End | Days | Status
Research | All | 2020-09-28 | 2020-10-02 | 4 | Complete
Planning | All | 2020-09-28 | 2020-10-02 | 4 | Complete
Data Collection | All | 2020-10-03 | 2020-10-05 | 2 | In Progress
Hardware and Installation | Jashan Singh | 2020-10-06 | 2020-10-16 | 10 | Not started
Network Connectivity | Amit Walia | 2020-10-17 | 2020-10-20 | 3 | Not started
Deploy Users | Jasmeet Singh | 2020-10-21 | 2020-10-23 | 2 | Not started
Setting DNS | Jasmeet Singh | 2020-10-24 | 2020-10-28 | 4 | Not started
Deploy Http | Amit Walia | 2020-10-29 | 2020-11-05 | 7 | Not started
Configuring LDAP | Amit Walia | 2020-11-06 | 2020-11-18 | 12 | Not started
Virtualization and Cloud | Jashan Singh | 2020-11-19 | 2020-11-25 | 6 | Not started
File Server | Jasmeet Singh | 2020-11-26 | 2020-11-28 | 2 | Not started
Final Testing | All | 2020-11-28 | 2020-11-30 | 2 | Not started
Technical Report | All | 2020-11-28 | 2020-11-30 | 2 | Not started
Demo | All | 2020-11-30 | 2020-12-04 | 4 | Not started
Launch

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address | Expectations
Amit Walia | Manager | Linux and Networking and online meetings | wali0031@algonquinlive.com | Successfully make connection between all machines and configure additional services and conduct schedule online meetings for discussion.
Jasmeet Singh | Manager | Windows and Management | sing1359@algonquinlive.com | Will manage the team and configure all things related to windows operating system .
Jashandeep Singh | Manager | Virtualization and Cloud | jash0001@algonquinlive.com | Will start soon installing and configuring VM's

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
House Meeting | 2hr Discussion | Planning of the Project | IN-person | One time | Amit | Jasmeet and Jashan
Online Meeting | Progress Discussion | Team management and divided work into tesammate | MS-teams | 2x a week | Amit | Jasmeet and Jashan